## README
Last Update | 2018-10-17
Author
Email
Description | CoinStalker
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
5 | Currency list | As a user, I want to see a list of all of the coins that I can track, so that I can explore cryptocurrency. More details: I also want to be able to favorite some currencies that I am interested in. | 6 | 1
8 | Currency details | As a user, I want to be able to tap specific currencies and see more details about that currency. More details: I want to see a graph of activity for that currency. | 3 | 2
4 | Dashboard | As a user, I want to see an overview of all of my tracked currencies, so that most of the information I want at a glance is in one place. More details: I want to see recent changes since I last opened the app and a graph of activity for my tracked currencies. | 6 | 3
10 | Exchange rate configuration | As a user, I want to be able to configure the program to display exchange rates in my local currency (USD, EUR, GBP, etc), so that the currency values are relatable. | 2 | 6
11 | Exchange rate calculator | As a user, I want to show the exchange rate between two different currencies of my choice, so that I can compare cryptocurrencies. | 1 | 7
1 | User account | As a person interested in using Coinstalker, I want to have the option to sign up for an account that syncs my tracked coins across multiple signed in devices, so that I don’t have to choose the currencies I’m interested in on each of my devices. More details: When I’m not logged in, my tracked coins are kept on my device instead of being synced. | 3 | 8
2 | Authentication API | As an unregistered user, I want to use my Facebook or Google account to log in to the app, so that I do not have to create a new account. | 2 | 8
3 | Registration | As an unregistered user, I want to use my email account with a password to log in to the app, so that I don’t have to link my other accounts to this service. | 2 | 8
12 | Push notifications | As a user, I want to receive notifications on my tracked currencies, so that I am kept up-to-date without needing to manually check the app. More details: I want to be able to set a percentage threshold for changes in the value of that currency, either up or down. | 5 | 8
6 | Currency filtering | As a user, I want to be able to search and filter the list of currencies, so that I can find the cryptocurrencies I am interested in. More details: I want to be able to filter by name and value. | 2 | 9
7 | Currency sorting | As a user, I want to be able to sort the list of currencies by different fields, so that I can compare cryptocurrencies. More details: I want to be able to sort by name, value, or volatility. | 4 | 9
9 | Share menu | As a user, I want to use the built-in share menu for my device to send currencies to my friends. More details: I want to send a message with the name of the currency, its current value, and a link that opens the Coinstalker app on that currency page. | 1.5 | 10
13 | Cryptocurrency news | s a user, I want to receive the latest news within the app about trending cryptocurrency news, so that I can stay informed and make educated decisions. | 4 | 10
14 | User commenting | As a user, I want to be able to converse with other users about topics relating to a specific cryptocurrency, so that I can find out more information about that currency and its trends. | 2 | 10
| Total |  | 43.5
Note on C2: Acceptance Criteria: 1. Displays alphabetically sorted list of all available currencies 2. Able to favorite currencies from the list
Note on C3: Acceptance Criteria: 1. Display exchange rate 2. Display growth rate graph 3. Display currency description
Note on C4: Acceptance Criteria: 1. Displays favorite currencies 2. Displays graphs for each currency 3. Able to jump to different screens in the app
Note on C5: Acceptance Criteria: 1. Display menu that allows the user to see what the cryptocurrencies value is in other national currencies.
Note on C7: Acceptance Criteria: 1. User table in database
Note on C8: Acceptance Criteria: 1. Once the Facebook/Google accounts are linked to the user table 2. Simple UI for signing in
Note on C9: Acceptance Criteria: 1. Able to create an account with an email address and password 2. Able to sign in with email address and password
Note on C10: Acceptance Criteria: 1. Can run app in the background polling for updates 2. Can push notifications for currency changes 3. Can set up what notifications you want to get
Note on C11: Acceptance Criteria: 1. Can type in fragment of currency name and have list change to show only matching currencies
Note on C12: Acceptance Criteria: 1. Can sort by rating 2. Can sort by name 3. Can sort by price 4. Can sort by volatility
Note on C13: Acceptance Critieria 1. Allow the user to share currency details via link
Note on C14: Acceptance Criteria: 1. Can pull content about cryptocurrency from news sources 2. Displays summaries of articles with links
Note on C15: Acceptance Criteria: 1. Logged in users are able to post comments on each currency 2. All users and view posted comments on the currency details screen

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Currency list (Jeremiah, Steve)
Currency details (Jeremiah, Steve)
Dashboard (Kenneth, Jeremiah)
Exchange rate configuration (Steve)
Exchange rate calculator (Steve)
User account (Patrick, Jaymar)
Authentication API (Patrick, Jaymar)
Registration (Patrick, Jaymar)
Push notifications
Currency filtering (Steve)
Currency sorting (Jeremiah)
Share menu
Cryptocurrency news
User commenting
Note on D5: Implement the DB with SQLite based on the design of account table Acceptance Criteria: 1. XXX 2. XXX Verified by: John Li

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Jeremiah | Task 5: Currency list
1 | Jeremiah | Task 6: Currency filtering
Note on C2: Design the login page, including the registration link

## Burndown Chart
Sprint ID | Total | Completed | Accumulated | Remaining | Ideal
1 | 43.5 | 8 | 0 | 35.5 | 35.5
2 | 43.5 | 0 | 0 | 43.5 | 43.5
3 | 43.5 | 0 | 0 | 43.5 | 43.5